## Sheet1
WinDU Task | System information on task error | Related info | PTC ticket | Comments | Post PTC Ticket Comment
DetectMasterWithDifferentContextDT | Property wt.containermove.owningorg.derivedFromContainer is set to false. | https://www.ptc.com/en/support/article/CS289720 | 16236383 | Need a PTC Ticket | No errors found can be skipped as its not a mandatory task
RevisionSequenceCleanserDT | Error: found master (SKU:10347, B - Black/Tech Grey : wt.part.WTPartMaster:3573812) with no iterations. Skipping master. | https://www.ptc.com/en/support/article/CS241974 | https://support.ptc.com/apps/case_logger_viewer/auth/ssl/case=16236386 | Need a PTC Ticket to confirm to proceed further | There are no issues reported in Source which PTC has listed if no issues reported this task is not mandatory
DanglingPBORef | Total corrupted tasks(workitems): 23 Total running processes with corrupted tasks: 0 Total processes(all states) with corrupted tasks: 8 | https://www.ptc.com/en/support/article/CS39937 | https://support.ptc.com/apps/case_logger_viewer/auth/ssl/case=16236389 | Suggestion to Ran the WinRU task DeleteWfProcessesHavingUnResolvablePBORef But need to see deletion is okay Further investigation needed | Reported WF are all terminated, Can be skipped for fixing
VerifyPrincipalDomain | Multiple issues |  | https://www.ptc.com/appserver/cs/view/case.jsp?n=16236391 | Confirmation from ptc to proceed ignoring this error | Solving discconnected principal issue solved this issue too
CabinetBasedDataContainerAlignmentReport | Diagnostic task reports all CabinetBased data that has a different container reference than the cabinet it lives in. The output of this task is a text file. | https://www.ptc.com/en/support/article/CS19027 | https://www.ptc.com/appserver/cs/view/case.jsp?n=16236392 | As per PTC This task is not pre-upgrade mandatory, it can be ignored. Confirmation needed from PTC | Not upgrade mandatory task for upgrade
PrincipalValidator |  |  | https://www.ptc.com/appserver/cs/view/case.jsp?n=16236396 | Confirmation from ptc to proceed ignoring this error | PTC Suggested to clean up Disconnected principal cleaning up the task was successful
PrincipalLocator |  | C16236397 | https://www.ptc.com/appserver/cs/view/case.jsp?n=16236397 | Proper cleanup instruction required | cs206075 Principal Locator is an information only Task not upgrade mandatory